## M-Omulimi
Feature | Responsible | Due | Status
Advisory | Herbert | 2020-10-16
Outbreaks & Crises | Herbert | 2020-10-16
Self Profiling | Herbert | 2020-10-16
GRM | Herbert | 2020-10-16
KMU/How To | Herbert | 2020-10-16
Push Notifications | Herbert | 2020-10-16
Weather & Pricing | Herbert | 2020-10-16

## M-Omulimisa
Feature | Responsible | Due | Status | PRIORITY
Advisory | Herbert | 2020-09-25 |  | HIGH
Outbreaks & Crises | Herbert | 2020-09-25 |  | HIGH
Profiling | Herbert | 2020-09-25 |  | HIGH
GRM | Herbert | 2020-10-02 |  | LOW
KMU/How To | Herbert | 2020-09-25 |  | HIGH
Push Notifications | Herbert | 2020-10-02 |  | LOW
Weather & Pricing | Herbert | 2020-10-02 |  | LOW
Email Notifications | Herbert | 2020-10-02 |  | LOW
Dashboard | Herbert | 2020-09-25 |  | HIGH
Extension Diary | Herbert | 2020-10-02 |  | LOW

## Omulimisa Dashboard
Feature | Responsible | Due | Status | priority
Digital Maps for Profiles | Herbert | 2020-10-02 |  | LOW
Outbreaks & Crises | Herbert | 2020-09-25 |  | HIGH
Profiling | Herbert | 2020-09-25 |  | HIGH
GRM | Herbert | 2020-10-02 | COMPLETED | LOW
KMU/How To | Herbert | 2020-09-25 |  | HIGH
Push Notifications | Herbert | 2020-10-02 |  | LOW
Weather & Pricing | Raymond | 2020-10-02 |  | LOW
Email Notifications | Herbert | 2020-10-02 |  | LOW
Dashboard | Herbert | 2020-02-10 |  | MEDIUM
Extension Diary | Herbert | 2020-10-02 |  | LOW
API | Raymond | 2020-10-02 |  | LOW
Flagging Issues | Raymond | 2020-09-25 |  | HIGH
Advisory | Herbert | 2020-09-25 |  | HIGH

## Omulimisa Web Portal
Feature | Responsible | Due | Status
FAQs | Raymond | 2020-11-06
Outbreaks & Crises | Herbert | 2020-11-06
Profiles | Herbert | 2020-11-06
Statistics | Raymond | 2020-11-06
KMU/How To | Herbert | 2020-11-06
Chatbot | ?? | 2020-11-06
Weather & Pricing | Raymond | 2020-11-06
Advisory | Herbert | 2020-11-06

## Support Data
Feature | Responsible | Due | Status
Subcounty GPS Location | Raymond/Thomas | 2020-10-01
Parishes GPS Location | Raymond/Thomas | 2020-10-01
SMS Gateway from MAAIF/Amos | Daniel | 2020-09-18
Authentication for the system | Raymond | 2020-09-18
KMU/How To Advisory Information | Daniel | 2020-10-23
Weather & Pricing API | Daniel | 2020-10-01